## Sheet1
SCHEDULED DELIVERY SHIP OPTION CREATION PLAN
Team involved | Configuration Requirements | Action | Start date | Duration | ETA | % of completion
Finance / DEX / Transportation | Project set up : Discuss the cost and financial details for the new ship option & fill out a requirements template | DEX/TRANS | JAN 2014 | 6 months | MAY 2014 | 100%
SIS | CIMS Proposal to create the ship option (rates, upgrades…) | DEX/TRANS | JULY 15 | 3 days | July 31st | ?
SD | Create specific FR string for Parcel : scheduleddelivery-dev generic | DEX
SD | Check how calendar jurisdictions are driving the display of the ship option | TRANS | fabrice
Ship Option created and available for testing
CSI | Update Blurbs, Help pages and Knowledge base to reflect new ship option for Non-Prime customers (if required) | DEX |  | 2 weeks
Transportation | Create a new ship method & map it to the ship option | TRANS | JUNE | 2 months | JULY 31st | 60%
DEX | Test ship option with test orders on the DEVO website | DEX | AUGUST | 2 weeks | AUG 15th
DEX | CX UI validation w/ Romain (# slots etc) | DEX | JULY | 1 day | JULY 31st
Transportation | Get the new ship option added to the right grouping for performance reports. | TRANS | AUGUST | 1 day | SEPT 15th
Transportation/CS | Consult with Concessions Team to set up the Concession Policy for the new ship option to be used by TRACES using a self-service tool | TRANS | AUGUST | 3 days
Supply Chain/Promise team | If necessary, specify new ship option as FT (+add it to FT order cutoff page). Usually done post creation, once performance has been demonstrated. | TRANS | SEPT | 2 weeks
Amazon Mobile | Configure the ship option to be available on wireless site | DEX |  | TBD
Shipping engine | Jeff Eakle (jeakle@) for changes/fixes required in SD Ship Charge plug-in | DEX
Shipping Integration | Dave Lane (davlane@) for configuring ship option and SPG rules | DEX/TRANS
ATROPS | Shyam Mishra – (shmishra@) – for configuring ship methods | TRANS
DEX | Robert Walde (rwalde@) - for testing/changes/fixes required in ship option grouping | DEX
RCX | Kai Liao (kailiao@) - for testing/changes/fixes required in check out for all devices | DEX
FXM | Chen Nicholas (nickchen@) - for changes/fixes required for refunds and related emails if any. | DEX
YA | Annie Groeninger (annieg@) – for changes/fixes required in YA for all devices if any. | DEX
CS Tech | Manmeet Dhody (manmeetd@) – for Order/Ship/Reschedule Confirmation Emails set up/modification if any. | TRANS
GTS | Debapriyo Ganguly (dganguly@) – for Manifest enhancements/fixes/set up if any. | TRANS
BITS | Vedhanarayanan Ganeshkumar (vganesh@) – for metrics support | DEX
Amazon Mobile | Integration of SD CX on mobile | CX mobile |  | TBD
Legal and PR | Ensure that customer facing communication is reviewed by legal and PR before going live | DEX |  | 2 weeks
GO LIVE |  |  |  | Pending SD team planning